## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | A user should be able to comment on any article on the Blog page in order to be able to interact and give opinions on certain topics | 1 | Mohamed | Bassant | Nadin
1.1 | After the signing up for TIQ membership,TIQ admin should be notified to approve or not on the new community member | 1 | Youssef | Nadin | Nada
1.2 | The user should be notified if his/her membership is approved or not | 1 | Nadin | Youssef | Bassant
1.3 | Approved memberships should have a full community access | 1 | Youssef | Nadin | Bassant
1.4 | Rejected memberships should remain as External with limited access | 1 | Youssef | Nadin | Bassant
2 | As a user I want to respond to debate live so that I can interact more on the website and have a full experience | 2 | Bassant | Youssef | Nada
2.1 | TIQ admins should be able to create the Debate lives (chaters, the motion, the date, number of responses ) | 2 | Nada | Youssef | Bassant
2.2 | TIQ admins should be able to delete the Debate lives | 1 | Menna | Bassant | Nada
2.3 | Users should be able to view the motions of the Debate lives | 1 | Kamal | Youssef | Menna
2.4 | Number of responses of a certain motion on the debate live should be updated dynamically | 1 | Bassant | Nada | Youssef
2.5 | Users should be able to mention each other within a certain motion in the Debate Live | 2 | Youssef | Nada | Bassant
2.6 | Users should be notifed that they are mention in a certain motion in the Debate Live | 1 | Youssef | Kamal | Menna
3 | Researching how to integrate with " IBM Watson API " for the chatbot | 3 | Menna
3.1 | Receive the messages from a client to be delivered to the server | 3 | Nadin
3.2 | Receive the messages from the server to be delivered to the client | 3 | Kamal
3 | Users should be able to search for other users by the name (either the first name or the last name) | 2 | Seif | Nouran | Nada
3.1 | Users should be able to search for other users by the type | 1 | Seif | Nouran | Nada
3.2 | Users should be able to search for articles by any word in the title | 2 | Nouran | Seif | Nadin
3.3 | Users should be able to search for motions of the chatbar by any word the title | 2 | Nouran | Seif | Nadin
TESTING USER STORIES
1 | Testing that the users can view other users | 1 | Nadin | Nouran | Seif
1.1 | Testing that the users can view a certain user | 1 | Nadin | Nouran | Seif
1.2 | Testing that the users are able to update their information probably | 1 | Nada | Nouran | Seif
1.3 | Testing that TIQ admins are able to update the information of the users probably | 1 | Nada | Menna | Bassant
1.4 | Testing that TIQ admins are able to create new users | 2 | Nada | Menna | Bassant
1.5 | Testing that TIQ admins are able to delete users | 1 | Nadin | Menna | Bassant
2 | Testing that users are able to view debates | 1 | Menna | Kamal | Bassant
2.1 | Testing that the users are able to view certain debates | 1 | Menna | Kamal | Bassant
2.2 | Testing that TIQ admins are able to create new debates | 2 | Menna | Kamal | Bassant
2.3 | Testing that TIQ admins are able to delete debates | 1 | Menna | Kamal | Bassant
2.4 | Testing that TIQ admins are able to update debates | 1 | Menna | Kamal | Bassant
3 | Testing that users are able to view Articles | 1 | Nada | Bassant | Mohamed
3.1 | Testing that users are able to view certain Articles | 1 | Nada | Bassant | Mohamed
3.2 | Testing that TIQ admins are able to create new Articles | 2 | Bassant | Nadin | Menna
3.3 | Testing that TIQ admins are able to delete Articles | 1 | Bassant | Nadin | Menna
3.4 | Testing that TIQ admins are able to update Articles | 1 | Bassant | Nadin | Menna
4 | Testing that users are able to view contents | 1 | Mohamed | Bassant | Youssef
4.1 | Testing that users are able to view certain content | 1 | Mohamed | Bassant | Youssef
4.2 | Testing that TIQ admins are able to create new content | 2 | Youssef | Kamal | Mohamed
4.3 | Testing that TIQ admins are able to delete content | 1 | Youssef | Kamal | Mohamed
4.4 | Testing that TIQ admins are able to update content | 1 | Youssef | Kamal | Mohamed
5 | Testing that users are able to view all the club on the HUB | 1 | Youssef | Kamal | Mohamed
5.1 | Testing that users are able to view certain clubs on the HUB | 1 | Kamal | Youssef | Bassant
5.2 | Testing that the HUB admin is able to create new clubs | 2 | Kamal | Youssef | Bassant
5.3 | Testing that the HUB admin is able to update the clubs | 1 | Kamal | Youssef | Bassant
5.4 | Testing that the HUB admin is able to delete clubs | 1 | Kamal | Youssef | Bassant
6 | Testing that users are able to view the FAQs | 1 | Seif | Nouran | Nada
6.1 | Testing that users are able to view certain FAQs | 1 | Seif | Nouran | Nada
6.2 | Testing that the HUB admin is able to create new FAQ | 2 | Nouran | Seif | Nada
6.3 | Testing that the HUB admin is able to update the FAQs | 1 | Nouran | Seif | Nada
6.4 | Testing that the HUB admins are able to delete FAQs | 1 | Seif | Nouran | Nada
7 | Testing that users are able to view the motions of the Debate live | 1 | Bassant | Nadin | Menna
7.1 | Testing that users are able to view certain motions of the Debate live | 1 | Youssef | Bassant | Menna
7.2 | Testing that TIQ admins are able to create new motions on the Debate live | 2 | Nada | Bassant | Nadin
7.3 | Testing that TIQ admins are able to delete motion from the Debate live | 1 | Bassant | Nada | Youssef
8 | Testing that the members' scores are always on update | 1 | Nadin | Bassant | Nada
8.1 | Testing that the number of responses are always updated | 1 | Nada | Bassant | Youssef
9 | Testing that user are able to search for debates by date and category | 1 | Seif | Nouran | Nada
9.1 | Testing that users are able to search for users by name and type | 1 | Seif | Nouran | Nada
9.2 | Testing that users are able to search for articles by any word in the title | 1 | Nouran | Seif | Nada
9.3 | Testing that users are able to search for motions on the debate live by any word in the title | 1 | Nouran | Seif | Nada