## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Users should be able to read content uploaded by the TIQ admin | 1 | Mohamed | Youssef | Kamal
1.1 | Users should be able to read users(the alumni's and mates') along with their brief description | 1 | Nada | Nadin | Bassant
1.2 | Users should be able to read debates | 1 | Menna | Bassant | Nada
1.3 | Users should be able to read other's profile | 1 | Nadin | Bassant | Mohamed
1.4 | Users should be able to read the FAQs | 1 | Nouran | Bassant | Seif
1.5 | Users should be able to read Clubs | 1 | Kamal | Youssef | Nada
1.6 | Users should be able to read articles | 1 | Youssef | Kamal | Bassant
1.7 | Users should be able to view the motions of the Debate lives | 1 | Bassant | Menna | Nada
2 | TIQ admin should be able to create users | 2 | Nada | Nadin | Bassant
2.1 | TIQ admins should be able to create debates | 2 | Menna | Nada | Bassant
2.2 | Hub admin should be able to create users (Admin of a certain AWG ) | 2 | Nadin | Bassant | Mohamed
2.3 | Hub admin should be able to create the FAQs | 2 | Nouran | Bassant | Seif
2.4 | Hub admin should be able to create new Clubs | 2 | Kamal | Youssef | Nada
2.5 | TIQ admins should be able to create articles | 2 | Youssef | Kamal | Bassant
2.6 | TIQ admins should be able to create the Debate lives | 2 | Bassant | Menna | Nada
2.7 | TIQ admins should be able to create content on the TIQ subdomain | 2 | Mohamed | Youssef | Kamal
3 | Hub admin should be able to update the FAQs | 1 | Seif | Bassant | Nouran
3.1 | Hub admin should be able to delete the FAQs | 1 | Seif | Bassant | Nouran
MISSING USER STORIES FROM THE BACKEND
1 | Users should be able to mention each other within a certain motion in the Debate Live | 1 | Youssef | Bassant | Nada
1.1 | Users should be notifed that they are mention in a certain motion in the Debate Live | 2 | Youssef | Bassant | Nada
NOTE: The previous 2 missing user stories were extra mentioned by Mayar( TIQ BOA ) and they weren’t mentioned from the beginning. It wasn't covered the previous sprint but will be implemented throughout this one.
2 | A user should be able to comment on any article on the Blog page in order to be able to interact and give opinions on certain topics | 1 | Bassant | Nada | Nadin