## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | TIQ admins should be able to create content on the TIQ subdomain | 1 | Kamal | None | None
1.1 | TIQ admins should be able to update content on the TIQ subdomain | 2 | Kamal | None | None
1.2 | TIQ admins should be able to delete content on the TIQ subdomain | 2 | Youssef | Kamal | As TIQ admin I should be able to create content then delete it
1.3 | Users should be able to read content uploaded by the TIQ admin | 1 | Youssef | Kamal | As TIQ admin I should be able to create content then view it
2 | TIQ admin should be able to create users(the alumni's and mates') along with a brief description | 1 | Nada | None | None
2.1 | TIQ admin should be able to update users(the alumni's and mates') information | 2 | Nada | None | None
2.2 | TIQ admin should be able to delete users(the alumni's and mates') with their information | 2 | Nadin | Nada | As TIQ admin I should be able to create alumni/mate then delete it
2.3 | Users should be able to read users(the alumni's and mates') along with their brief description | 1 | Nadin | Nada | As TIQ admin I should be able to create alumni/mate then view it
3 | TIQ admins should be able to create debates | 1 | Menna | None | None
3.1 | TIQ admins should be to update debates | 2 | Menna | None | None
3.2 | TIQ admins should be able to delete debates | 2 | Menna | None | None
3.3 | Users should be able to read debates | 1 | Kamal | Menna | As a hub admin I should be able to create user then delete it
4 | Hub admin should be able to create users (Admin of a certain AWG ) | 1 | Nadin | None | None
4.1 | Users and Hub admin should be able to update the user profile | 2 | Bassant | Nadin | As a hub admin I should be able to create user then update it
4.2 | Hub admin should be able to delete a user | 2 | Bassant | Nadin | As a hub admin I should be able to create user then delete it
4.3 | Users should be able to read other's profile | 1 | Bassant | Nadin | As a hub admin I should be able to create user then view it
5 | Hub admin should be able to create the FAQs | 1 | Nouran | None | None
5.1 | Hub admin should be able to update the FAQs | 2 | Nouran | None | None
5.2 | Hub admin should be able to delete the FAQs | 2 | Seif | Nouran | As a hub admin I should be able to add FAQs then delete it
5.3 | Users should be able to read the FAQs | 1 | Seif | Nouran | As a hub admin I should be able to add FAQs then view it